## Document Control
ELYON SOLUTIONS INTERNATIONAL INC.
User Acceptance Testing (UAT) Test Script
Client-Specific Requirement Enhancement – Merge Pallet Feature
DOCUMENT INFORMATION
Document Title | Merge Pallet Feature – UAT Test Script | Version | 1.1
System | VIFEL Odoo 17 Enterprise – WMS | Status | For UAT Execution
Module | vifel_client_requirements (Merge Pallet) | Environment | UAT / Staging
Prepared By (Vendor) | Elyon Solutions International Inc. | Date | 02-Aug-2026
Prepared For (Client) | Vifel Ice Plant & Cold Storage, Inc. | Reference | VIFEL-CR-MergePallet
1. PURPOSE
This test script lets Vifel Ice Plant & Cold Storage, Inc. confirm that the Merge Pallet feature delivered by Elyon Solutions International Inc. behaves correctly against the agreed business requirements. Each row is a real business scenario phrased as a question; the tester performs it and records whether the system's behaviour matches the Expected Result.
2. HOW THIS SCRIPT IS ORGANISED
The 'Test Cases' sheet is grouped by OPERATION TYPE so you test one activity fully before moving on — no jumping back and forth: (A) Setup & Configuration → (B) Receiving (RR) → (C) Withdrawal (WR) → (D) Reports & Count Integrity. Do the setup once, then work each coloured section top-to-bottom. Record Actual Result, set Status from the drop-down, and note any issue in Remarks.
3. STATUS LEGEND
Pass | Behaviour matches the Expected Result.
Fail | Behaviour differs; log the issue in Remarks.
Blocked | Cannot be executed (dependency / defect).
Not Executed | Not yet run.
4. REVISION HISTORY
Version | Date | Author | Description
1.0 | 28-Jul-2026 | Elyon Solutions | Initial scenario-based UAT test script.
1.1 | 02-Aug-2026 | Elyon Solutions | Grouped by operation type; added Lot No./Batch #/Prodcode cases.

## Test Cases
MERGE PALLET FEATURE – UAT SCENARIO CHECKLIST (BY OPERATION TYPE)
Elyon Solutions International Inc. • Client: Vifel Ice Plant & Cold Storage, Inc. • Version 1.1
Ref | Requirement / Feature | Priority | Scenario Question (What we are verifying) | How to Test | Expected Result | Actual Result | Status | Remarks
A. SETUP & CONFIGURATION (do once)
MP-A1 | Client Setup | High | When a Vifel client is switched on for merging, do the merge options appear only for that client? | On the client's contact, tick 'Can Merge Pallets' in the VIFEL Configuration tab and save. Open a receipt for this client, then for a different (non-enabled) client. | The VIFEL Configuration options and the Merge feature appear ONLY for the enabled client; other clients are unaffected. |  |  |  | g
MP-A2 | Client Setup | High | Can we set the two merge modes — Fixed (one pinned pallet) and Multiple (special PSI types)? | For one client set Fixed mode + pin a pallet and a Fixed PSI. For another, tick Multiple Pallet Support and confirm the PSI types (MDGM/SDMG/TDMG/BOC) auto-seed. | Fixed mode saves the pinned pallet + PSI; Multiple mode shows the special PSI types with descriptions. |  |  |  | g
MP-A3 | Client Setup | Medium | Do the Lot No. and Batch # / Prodcode columns switch on per client from the profile? | Tick 'Show Lot No.' and 'Show Batch # / Prodcode' for the client, save, and open its Pallet Breakdown. | The Lot No. and Batch # columns appear for this client only; other clients don't see them. |  |  |  | g
B. RECEIVING (RR)
MP-B1 | Fixed Pallet | Critical | For a Fixed client, does the FIRST stock onto the empty pinned pallet count as a received pallet (+1), and a later receipt as +0? | Merge Pallet onto the empty pinned pallet, validate, check the count. Then on a NEW RR merge onto the now-stocked pinned pallet and check again. | The first stock counts +1 (it births the pallet); the later receipt merges +0 (no new pallet). Weight/Qty/Packs count in full both times. |  |  |  | g
MP-B2 | New Special Pallet | High | Starting a NEW special pallet (e.g. SDMG) — is it counted as +1, and is its location limited to the receipt's building? | On an RR line choose 'Start a New Special Pallet', pick a PSI type, an empty pallet and a location. Try a location in another building, then a valid one; confirm and check the count. | Only locations under the receipt's destination building are offered/accepted; the new pallet counts as ONE received pallet (+1). |  |  |  | g
MP-B3 | Merge on Receipt | Critical | On merge of an existing PSI pallet, does it NOT add a pallet to the count (+0)? | On an RR line, click 'Merge Pallet' and pick an existing stocked pallet. Confirm. Compare the received pallet count before and after. | The line adopts the target's Pallet Series and location; it is flagged 'Merged'; the received pallet count does NOT increase (+0). |  |  |  | g
MP-B4 | Merge on Receipt | High | When a line is merged (+0 pallet), do Weight (KG), Quantity and Packs still count in full? | Review a merged line's Weight (KG), Quantity and Packs after the merge. | Weight (KG), Quantity and Packs are recorded in full. Only the pallet count is +0; the goods are not lost. |  |  |  | g
MP-B5 | Same-Receipt Merge | Critical | If two lines of the SAME receipt sit on one pallet (New PSI), is that counted as ONE pallet (+1), not two? | On line 1 assign/start a pallet(New PSI). On line 2 click 'Merge Pallet' and choose line 1's pallet ('On this receipt'). Validate and check the received count. | Both lines share one pallet and Pallet Series; the receipt counts them as exactly ONE received pallet (+1). Both lines show 'Merged'. |  |  |  | g
MP-B6 | Un-merge | High | Can a merged / shared line be Un-merged on a receipt, and does the pallet count stay correct? | On a line that shows 'Merged', click 'Un-merge'. Observe the line and the pallet; re-check the count. | The line is peeled off to its own blank pallet (re-assign a series); the other line keeps the pallet; the pallet count stays correct.
MP-B7 | Merge Wizard | Medium | In the merge wizard, if I toggle a second 'Merge Here' pallet, does the first one switch off (only one target)? | Open Merge Pallet. Toggle 'Merge Here' on one candidate pallet, then on a second candidate. | Only one 'Merge Here' can be active at a time; selecting a second switches the first off. The system never merges onto two pallets.
MP-B8 | Lot No. / Batch # | High | Does the Lot No. really reflect — is the Lot No. typed on a receiving line saved onto stock? | Enter a Lot No. on an RR line. Validate the RR. Open Inventory → the resulting stock (quant). | The Lot No. stays on the line and is stamped onto the received stock; it is visible on the quant.
MP-B9 | Lot No. / Batch # | High | Does the Batch # become a Prodcode (DDMONYYYY + Batch # + Building) at validation — WITH the building shortname at the end? | Enter a Batch # (e.g. 99) on an RR line that has a expiration date. Validate. Inspect the Prodcode on the stock (quant). | The Prodcode is day+month+year+Batch#+building short name, e.g. 18MAY202699M — the building short name IS present at the end for every building.
C. WITHDRAWAL (WR)
MP-C1 | Partial Withdrawal | Critical | On WR, can a merge pallet be PARTIALLY withdrawn, and does it count -0 (only -1 when fully emptied)? | Create a WR that withdraws SOME of the products on a merge pallet, leaving others. Validate. Then fully empty the pallet on another WR. | The partial withdrawal is allowed (no 'still has available quantity' block) and counts -0. The pallet counts -1 only when fully emptied.
MP-C2 | Lot No. on WR | High | On withdrawal, does the Lot No. that was set at receiving get PULLED onto the WR Pallet Breakdown? | Withdraw stock that had a Lot No. set at receiving. Open the WR Pallet Breakdown and show the Lot No. column. | The Lot No. frozen at receiving is displayed (read-only) on the matching withdrawal line — it is no longer blank.
MP-C3 | Prodcode on WR | Medium | On withdrawal, does the Prodcode created at receiving show on the WR Pallet Breakdown? | Withdraw stock that has a Prodcode. Open the WR Pallet Breakdown and show the Prodcode column. | The Prodcode frozen at receiving is displayed (read-only) on the matching withdrawal line.
MP-C4 | Multi-truck | High | For a pallet shared across trucks, does it count on the truck that EMPTIES it (not the first truck)? | Split one pallet across two WRs (one leaves stock, the next takes the rest). Validate both; check which WR counts the pallet. | The pallet counts once, on the WR whose validation leaves the pallet empty; the truck that left stock counts it -0.
D. REPORTS & COUNT INTEGRITY
MP-D1 | Count Integrity | Critical | Does a merge / shared pallet count as exactly ONE pallet end-to-end? | For a merge pallet, review the RR received count, the pallet-kilos (PKR) ledger, and the WR/RR printout. | The merge pallet is counted as exactly ONE pallet in the receipt, the ledger, and the printed reports.
MP-D3 | Stock View | Medium | Can Lot No., Batch # and Prodcode be looked up in the Inventory (stock) view? | In Inventory → Stock, enable the optional Lot No., Batch # and Prodcode columns. | All three columns are available in the stock view and show the values frozen at receiving.
ACCEPTANCE SIGN-OFF
[5 empty] | Role | Name | Signature | Date
[5 empty] | Prepared by (Elyon) | Mark Angelo Templanza
Tested by (Vifel)
Reviewed by (Vifel)
Approved by (Vifel)

## Summary & Sign-off
EXECUTION SUMMARY & ACCEPTANCE SIGN-OFF
RESULT | COUNT | % OF TOTAL
Total Test Cases | 22 | 100%
Pass | #REF! | #REF!
Fail | #REF! | #REF!
Blocked | #REF! | #REF!
Not Executed | #REF! | #REF!
Overall Pass Rate | #REF!
OVERALL UAT ASSESSMENT
☐ Accepted
☐ Accepted with Conditions
☐ Rejected
Remarks / Conditions:
ACCEPTANCE SIGN-OFF
Role | Name | Signature | Date
Prepared by (Elyon)
Tested by (Vifel)
Reviewed by (Vifel)
Approved by (Vifel)